## Reg 40A
Proposed Timelines & Event Chart (As per Regulation 40A)
S.No | CIRP Task | Norm | Legal timeline | Due as per timelines | Actual timelines | Remarks if any |  | 2023-04-25
Duties of IRP
| CIRP commencement date and Appointment of IRP | - | T | 2023-04-25
| Public announcement inviting claims | Within 3 Days of Appointment of IRP | T+3 | 2023-04-28
| Submission of claims under Regulation 12(1) | On or before last date mentioned in public announcement | T+14 | 2023-05-09
| Verification of claims received under Regulation 12(1) | Within 7 days from the receipt of the claim | T+21 | 2023-05-16
| Submission of claims under Regulation 12(2) | within 90 days of ICD | T+90 | 2023-07-24
| Verification of claims received under Regulation 12(2) | Within 7 days from the receipt of the claim | T+97 | 2023-07-31
| Report certifying constitution of COC | Within 2 days from verification of claims received under regulation 12(1) | T+23 | 2023-05-18
| 1st meeting of the COC | Within 7 days of the constitution of the COC, but with seven days’ notice | T+30 | 2023-05-25
| Resolution to appoint RP by the CoC | In the first meeting of the CoC | T+30 | 2023-05-25
| Appointment of RP | On approval by the AA | - | -
Duties of RP
| Appointment of RP | On approval by the AA | -
| Appointment of valuer | Within 7 days of appointment of RP, but not later than 40th day of commencement | T+47 | 2023-06-11
| Submission of IM to COC | Within 2 weeks of appointment of RP, but not later than 54th day of commencement | T+95 | 2023-07-29
| Publish Form G | Within 60 days of commencement | T+60 | 2023-06-24 | 08.Jul-23 | On or before | 2023-07-08
| Invitation of EOI |  | T+60 | 2023-06-24 |  | On or before
| Submission of EOI | At least 15 days from issue of EOI (Assume 15 days) | T+75 | 2023-07-14 | 2023-07-24 |  | 2023-07-23
| Provisional List of RAs by RP | Within 10 days from the last day of receipt of EOI | T+85 | 2023-07-19 | 2023-07-28 |  | 2023-07-27
| Submission of objections to provisional list | For 5 days from the date of provisional list | T+90 | 2023-07-24 | 2023-08-02 |  | 2023-08-01
| Issue of RFRP, including Evaluation Matrix and IM | Within 5 days of the issue of the provisional list | T+90 | 2023-07-24 | 2023-08-02
| Final List of RAs by RP | Within 10 days of the receipt of objections | T+100 | 2023-08-03 | 2023-08-03 |  | 2023-08-03
| Receipt of Resolution Plans | At least 30 days from issue of RFRP (Assume 30 days) | T+120 | 2023-09-02 | 2023-09-02 |  | 2023-09-02
| Submission of COC approved Resolution Plan to AA | As soon as approved by the COC | T+165
| RP to form an opinion on preferential and other transactions | Before 75th day of commencement date | T+75 | 2023-07-09 |  | Appointment of transaction auditor
| RP to make a determination on preferential and other transactions | Before 115th day of commencement date | T+115 | 2023-08-18
| RP to file applications to AA for appropriate relief | Before 135th day of commencement date | T+135 | 2023-09-07 |  | CIRP 8 to be filed
| Approval of resolution plan by AA |  | T=180 | 2023-10-22
2024-01-20
2024-03-20
Formulas:
Due as per timelines = [Due as per timelines, row above]+60

## Pin board
PERFECT ENGINEERING PRODUCTS LIMITED CIRP COMMENCEMENT DATE: 06.06.2023
Event | Model Timeline as per Reg. 40A
CIRP commencement date and Appointment of IRP | 06.06.2023
Public announcement | 08.06.2023
Last date to submit the claim | 20.06.2023
Report certifying constitution of COC | 29.06.2023
1st meeting of the COC | 06.07.2023
Appointment of RP | 06.07.2023 | File CIRP-2 If not file CIRP-7
Submission of IM to COC |  | File CIRP- 3 If not file CIRP-7
Publish Form G
Issue of RFRP, including Evaluation Matrix and IM |  | File CIRP-4 If not file CIRP-7
RP to make a determination on preferential and other transactions |  | If not File CIRP-8
180 days |  | On completion of process File CIRP-5 If not File CIRP-7